# Drug and Alcohol Needs Assessment: Recommendations and Actions Summary

# Our Gloucestershire Recommendations and Actions

The findings and new insights available from an in-depth assessment of the data available to us enabled the development of a draft Needs Assessment and suggested recommendations. These were shared with stakeholders for discussion and development. Ten priority recommendations were identified for focus over the next 3 years.

| Priority | Recommendation |
| --- | --- |
| 1 | Respond to the rising prevalence of ketamine use |
| 2 | Improve equity of access |
| 3 | Take a more integrated approach to co-occurring mental health & substance use needs |
| 4 | Improve treatment outcomes |
| 5 | Reduce alcohol-related harm |
| 6 | Improve Individual Placement Support |
| 7 | Identify and support vulnerable families |
| 8 | Work in partnership to reduce harm |
| 9 | Develop system workforce training |
| 10 | Address complex, high and overlapping needs |

## 1. Respond to the rising prevalence of ketamine use

| Actions | Lead | Impacts | Draft Measures & Deliverables | Resources | By When |
| --- | --- | --- | --- | --- | --- |
| Educating professionals and the wider public about the effects of ketamine | Ketamine Task & Finish Group | Increased awareness of ketamine and associated health harms Better early identification Increased timely referrals for treatment | Deliver ketamine awareness webinar and other materials to professionals (attendance at webinar) Increase the number of ketamine-related discussions, screenings or brief interventions recorded by frontline services by 20% (service activity data) Increase the number of appropriate referrals to drug & alcohol treatment services where ketamine is identified as the primary of secondary substance by 15% (treatment provider referral data) | £15,000 over the next three years for education and campaign materials | March 2027 March 2027 March 2027 |

## 2. Improve equity of access

| Actions | Lead | Impacts | Draft Measures & Deliverables | Resources | By When |
| --- | --- | --- | --- | --- | --- |
| Map potential community hubs | Adult Treatment Planning Group | Improved understanding of barriers Enhanced multi-agency working Increased take-up and completion of treatment | Countywide mapping exercise identifies at least 10 potential community hubs suitable for delivering support services Pilot service delivery in 2 community hubs in areas of identified need | £99,000 over the next three years | March 2027 March 2028 |
| Develop an open access directory of services | Adult Treatment Planning Group | Enhanced multi-agency working Increased take-up and completion of treatment | Up-to-date directory is shared with all partners Increased referrals from priority partner agencies (e.g. primary care, mental health services, schools, colleges, housing, social care and criminal justice services) by 10% by March 2028 (NDTMS outcome data) |  | Summer 2027 |
| Expand peer mentoring | Adult Treatment Planning Group | Increased retention in treatment and completion of treatment | Peer mentors are recruited and trained Treatment progress measures sustained Treatment completion measure improved for target cohorts |  | Ongoing 2026 - 2029 |
| Review digital and written materials | Adult Treatment Planning Group | Increased referrals into treatment | GCC website content is updated to include direct links to services, LDIS and Action Plan Increase referrals from priority partner agencies (e.g. primary care, mental health services, schools, colleges, housing, social care and criminal justice services) and the wider public by 10% by March 2028. |  | Winter 2026 |

## 3. Take a more integrated approach to co-occurring mental health & substance use needs

| Actions | Lead | Impacts | Draft Measures & Deliverables | Resources | By When |
| --- | --- | --- | --- | --- | --- |
| Re-establish Co-Occurring Conditions Steering Group | COSUM Sub-Group | Stronger multi-agency working More integrated services and pathways Increased representation of people with lived experience Better outcomes for service users/patients | A multi-agency Group with agreed terms of reference, membership and governance is in place by Autumn 2026 A minimum of 4 meetings per year, with at least 75% attendance | £108,000 over the next three years | Autumn 2026 |
| Complete self-assessment | COSUM Sub-Group | Improved understanding of current system strengths and gaps which provides a clear baseline Shared understanding of roles, responsibilities and referral routes Increased collaboration between services | The Group completes a self-assessment of system capabilities, strengths and weaknesses by Spring 2027. An Action Plan based on the findings of the self-assessment is developed and approved, to include at least 5 systemwide priority actions |  | Spring 2027 Details tbc |
| Review pathways of support | COSUM Sub-Group | More streamlined and clearly defined referral, treatment and support pathways Reduced barriers to accessing support Better workforce confidence and competence Identification of training needs | Review and consider revising all relevant referral pathways and shared care protocols for people with co-occurring conditions Implement pathway changes Achieve 75% positive service-user feedback regarding ease of access and navigation of co-occurring conditions services (service user surveys) |  | Autumn 2027 Throughout 2028 Spring 2029 |

## 4. Improve treatment outcomes

| Actions | Lead | Impacts | Draft Measures & Deliverables | Resources | By When |
| --- | --- | --- | --- | --- | --- |
| Explore substance-specific programmes | Adult Treatment Planning Group | Increase in achievement against treatment progress and treatment completion measures Reduced relapse | Undertake benchmarking with at least 3 local authorities/treatment systems Design & launch at least one new substance-specific product or pathway (depending on the result of the review and benchmarking) | Additional posts to Mar 2029 £120,000 Buvidal £75,000 lived experience initiatives | By Spring 2027 By Spring 2028 |
| Recovery check-ins and relapse support | Adult Treatment Planning Group | Reduced relapse rates Improved treatment completion rates Increased retention and re-engagement rates | Offer recovery check-ins to 75% of individuals within 3 months of treatment completion Increase in treatment completion rate for adults Sustain treatment completion rates for young people |  | By Summer 2027 By Spring 2029 |

## 5. Reduce alcohol-related harm

| Actions | Lead | Impacts | Draft Measures & Deliverables | Resources | By When |
| --- | --- | --- | --- | --- | --- |
| Explore technologies Increase detox and rehabilitation Fund prevention work with young people | Adult Treatment Planning Group DARD Group Children & Young People's Group | Earlier identification and intervention More support available Better understanding among young people about the short- and long-term risks associated with alcohol use | Review of early support apps is completed. Potentially app support commissioned depending on the outcome of the review. Additional placements into rehab Fewer young people report using alcohol below the age of 18 (Pupil Wellbeing Survey) | £106,000 additional rehabilitation budget | March 2027 March 2028 March 2028 2028 |

## 6. Improve Individual Placement Support

| Actions | Lead | Impacts | Draft Measures & Deliverables | Resources | By When |
| --- | --- | --- | --- | --- | --- |
| Extend professional networks | IPS Steering Group | Improved recovery and social inclusion Reduced relapse Improved financial wellbeing | Increased employment, training and volunteering opportunities for people in recovery Increase in the number of service users starting jobs to 30 annually and those sustaining employment at 13 weeks to 20 annually | £495,751 over three years | By March 2029 |
| Develop employer relationships | IPS Steering Group | Improved recovery and social inclusion Reduced relapse Improved financial wellbeing | Establish new partnerships with at least 20 local employers |  | By March 2028 |

## 7. Identify and support vulnerable families

| Actions | Lead | Impacts | Draft Measures & Deliverables | Resources | By When |
| --- | --- | --- | --- | --- | --- |
| Set up Hidden Harm Group | Public Health Commissioners | No Wrong Door approach Harm reduction Improved family support | Multi-agency group is established, meeting at least quarterly with consistent attendance from at least 75% of members | FDAC funding maintained Specialist Midwifery post | By Autumn 2026 |
| Early intervention for pregnant women | Hidden Harm Group | Earlier identification of women who are pregnant and affected by substance use Improved support for pregnant women Improved outcomes for babies | Harm reduction/ brief intervention pathways identified and delivered by midwives and/or in partnership with Via and Nelson Trust Increase referrals from midwifery into specialist services |  | By Spring 2027 |
| Enhance family interventions | Children & Young People's Group | Stronger multi-agency working delivers improved outcomes for parents, children and young people Improved safeguarding Reduced intergenerational harm – improved family stability and resilience | 90% of identified families receive an assessment/offer of support within 4 weeks of referral More staff trained in CRA-FT |  | By Summer 2027 |

## 8. Work in partnership to reduce harm

| Actions | Lead | Impacts | Measures & Deliverables | Resources | By When |
| --- | --- | --- | --- | --- | --- |
| Strategic Planning Day | Adult Treatment Planning Group | Better partnership working Reduced duplication Joint working measures | Stakeholders will agree 3 priority objectives for substance use prevention, treatment and recovery, with at least 80% participant consensus captured through voting or feedback. | MEAM and MARM programmes | 2028 |
| Develop shared tools and pathways | Adult Treatment Planning Group | Improved identification of vulnerable people More timely information sharing between partner organisations Reduced duplication of assessments and improved service user experience | Increased uptake of interventions such as naloxone provision, brief interventions and needle exchange MDT established for people who are rough sleeping and using drugs and/or alcohol |  | Summer 2028 Autumn 2026 |
| Wound Awareness Workshop | Public Health Commissioners | Better partnership working and understanding of the Gloucestershire system Reduced harm to vulnerable cohort | Attendees report greater awareness of risk factors and early signs plus understanding of escalation pathways (delegate feedback form) |  | Summer 2026 |

## 9. Develop system workforce training

| Actions | Lead | Impacts | Measures & Deliverables | Resources | By When |
| --- | --- | --- | --- | --- | --- |
| Peer-to-peer training programme | Adult Treatment Planning Group | Increased staff knowledge and understanding of substance use, harm reduction and recovery Greater consistency in advice provided to service users Improved sustainability of learning through ongoing peer support | Multi-disciplinary training programme is co-produced and agreed by Spring 2027 and in delivery by Summer 2027 75% of staff who receive training report increased confidence (training feedback forms) 75% of peer trainers deliver at least one session within their host organisation | £200,000 workforce development funding | From 2027 |
| People with lived experience are included in training (including the planning of training materials) | LERO Development T&F Group | Training which increases understanding of realities and complexities of substance user More person-centred and trauma-informed care and support Reduced stigma, stereotypes and judgemental attitudes | 75% of training participants report increased understanding and confidence (training feedback forms) 100% of people with lived experience who are involved in the work report that they feel listened to and have their views included in the training |  | From 2027 |

## 10. Address complex, high and overlapping needs

| Actions | Lead | Impacts | Measures & Deliverables | Resources | By When |
| --- | --- | --- | --- | --- | --- |
| Recruit additional outreach capacity to support people who are rough sleeping and experiencing substance user | RSDAT Project Group | Earlier identification of people at risk of rough sleeping and substance use results in increased access to treatment and recovery support Improved engagement with services among high-risk groups Improved data-sharing arrangements are in place | Additional workforce is in place to include outreach workers, a nurse prescriber and accommodation-based support worker | £909,148 RSDAT funding plus CHPSS and MEAM support | Autumn 2026 Autumn 2026 Autumn 2026 |
| Develop specialist housing provision | RSDAT Project Group | Embedded detox housing pathways | Accommodation which provides wraparound support for people in alcohol detox is secured in Gloucester, providing x 2 beds at any one time (Emerging Futures) |  | By Spring 2027 |