| Activity Card one: Children will thrive GCP Sponsor: Jo Grills |  |  |  |
| --- | --- | --- | --- |
| Reporting Lead: Ruth Lewis |  |  |  |
| Priority outcomes |  |  |  |
| - Families and young people are well informed to help themselves - Children and family’s needs are met in their local communities - As problems emerge, as far as possible, children and family’s needs are met in universal services |  |  |  |
| Outcomes | Improvement / change activity | Base line/ target | Lead |
| Families, young people and practitioners are well informed to help themselves | Early Help Information and Local Offer are made robust and accessible through the Glos Families directory | SEN D Local Offer fully compliant and updated periodically. | Alison Cathles GCC |
|  | Drop-in community hubs established for those with a disability to access information for example employment and independence options Two Drop In/s to become user led as part of a ‘pilot’ for 1 year. These will be Gloucester and Forest. | 2 hubs initiated in 2016 2 hubs to commence as a pilot from May 2016 for 1 year and then to be reviewed. | Dena Boucher GCC |
| Children and family’s needs are met in their local communities | Parent champions will provide information and support to work alongside parents to improve outcomes for families and to inform the reshaping of services for families with young children. | Baseline: 9 parent champions currently active across LA. Target: Pilot has been extended for another year to increase to 12 parent champions by September 2016. | Wendy Rycroft GCC |
| As problems emerge, as far as possible, children and family’s needs are met in universal services | Increase levels of school attendance in lowest attaining schools | Levels of attendance are increased and persistent absence is reduced in the 30 schools with the lowest rates | Jane Lloyd-Davies` GCC |
|  | To help identify problems early we will develop a single Early Help pathway, to replace the common assessment framework (CAF) for all children and young people with additional needs. | Pathway implemented September 2016 | Sarah Spurway GCC |
|  | Embed and evaluate the impact of the early intervention Positive Behaviour Support service in all settings. | Impact review September 2015 | Amanda Henderson/Alison Cathles |
|  | Work together in developing a pilot Early Years integrated service based on: - Children’s Centre services - Health visiting - Community midwifery | Aligned working in three localities is operational in 2016 | Ruth Lewis GCC |
|  | Process for identification of children’s additional needs in their early months and years | Multi-agency process is developed and in place in 2016 | Sarah Birmingham Glos Care Services NHS Trust Sarah Hylton GCC |
|  | Police front line staff have latest training to identify children at risk and take appropriate action working with partners, in line with ‘Working Together guidance’ | Public protection training programme and guidance in place for front line staff in 2016. Supported by Safeguarding Champions in key roles | DS Simon Atkinson Police |
| What Partners are going to do: |  |  |  |  |
| - Use the Family Information Service (FIS) to provide Early Help information for families’ young people and practitioners. - Put a multi-agency Early Help Strategy in place - Actively endorse and support the all age all disability Building Better Lives strategy - Provide an ‘enabling function’ for universal services from District led Early Help Hubs - Ensure children and young people access their full education entitlement - Successfully transfer the commissioning responsibility for the health visiting service from NHS England to GCC Public Health - Refresh the Early Years commissioning framework in the context of the wider Framework for 0-18 - District Councils work with families at risk to prevent homelessness - Work together to raise expectations of levels of employment with families and young people, including those with a learning difficulty or disability - Enable collaborative and integrated working, commissioning, training and development opportunities - Safely share planning, knowledge, information, data and good practice to address issues, inform, intervention and improve outcomes, appropriate to differing needs in areas of the county - Acknowledge and develop differentiated approaches across the county to reflect the differing needs and assets in localities and Districts - District Councils will support provision of youth activity and engagement with local partners |  |  |  |  |
| Resources: GCC; CCG; Public Health; Police; Glos Care Services NHS Trust Key risks: Reduced workforce capacity; reduced levels of funding; rising demand |  |  |  |  |