## Action Plan
Corporate Peer Challenge 2023 - Action Plan Our responses to the feedback of the Local Government Association (LGA) Peer Team
Rec. No. | Key Recommendation | CLT Owner | Actions | Action Owner | How do we measure improvement for November 2024 | Progress Check End Aug 24 | Progress Check Nov 2024
1 | Build on the council’s strategic leadership role to work with partners to shape the evolution of a refreshed vision for growth in Gloucestershire | Director of Economy and Environment | The new City Region Board has been established as a Joint Committee of the County Council and the six District Councils within Gloucestershire as a key driver of our vision for growth. | Director of Economy and Environment | Feedback/action points from meetings. First mtg May/June | First meeting of the City Region Board took place on 7th June 2024. It was agreed that the Director of Economy and Environment would visit district authorities to present the economic strategy ahead of noting the strategy in September 2024. | Leadership Gloucestershire conference event was held on 'system Leadership' 8th Nov 2025: It was agreed to identify a co-design group for future collaborative planning, and to use the co-design group to plan for a ‘values and behaviours’ session in February 2025 facilitated by Leadership Centre.
|  |  | The emerging Economic Strategy (which is the next evolution of, and supercedes the previous Vision 2050 work) includes Sustainable Economic Growth as one of it's four themes and this will be subject to a deep dive exercise at the first meeting of the City Region Board. | Director of Economy and Environment | Minutes of first meeting of City Region Board | Economic Strategy approved by GCC cabinet in May 2024 and will be noted by district authorities at the City Region Board meeting on 5th September 2024. Director of Economy and Environment and Lead Cabinet member have visited district partners to present the economic strategy and identify common priorities. | Gloucestershire Economic Strategy was noted by all seven local authorities at the City Region Board on 5th September 2024 and it was agreed that it would be used to set the agenda for future meetings.
|  |  | Local Economic Partnership (LEP) transition carefully managed to ensure ongoing strong connections to businesses and support for district growth hubs | Director of Economy and Environment | signed off by Cabinet in November, to transfer on 1st April | Local Enterprise Partnership staff transferred on 1st April 2024. All activity continues to be delivered. Director of Economy and Environment reviewing all services to business and the economy. | LEP fully transferred. Services being reviewed currently in the light of Government budget announcements.
|  |  | Economic Strategy emerging and plans underway for an Economic Growth Board to increase engagement with districts, business, education, and the Voluntary & Community Sector (VCS). | Director of Economy and Environment | Minutes of first meeting of Economic Growth Board | First meeting of the Economic Growth Board will be on 5th September 2024. | First meeting held on 5th September to present economic strategy and national policy picture. Next meeting planned for January 2025.
2 | Prioritise the continued investment in IT as an enabler to the council’s operations and make its improvement a demonstrable and equal part of the council’s overall transformation portfolio, with associated funding, expertise and leadership | Executive Director of Corporate Resources | Medium Term Financial Strategy (MTFS) makes investments of £1.2m revenue (of which £856k is recurring) and a further £13.4m of capital funding over the lifetime of the programme | Director of People and Digital Services | Delivery against areas of investment included in MTFS | The ICT improvement programme continues to deliver improvements to infrastructure and day to day experience for staff and residents. The next phases of the roadmap have been developed with progress meaning that there can be new focus on digital innovation and skills as well as the basics. The capital funding programme has been reviewed and further investment will be considered during the Medium Term Financial Strategy planning. | Delivery of the ICT roadmap continues against the significant investment already agreed. Bringing Enterprise Support inhouse has reduced cost and therefore released additional funding for digital innovation. Medium Term Financial Strategy proposed budget includes additional investment to enhance the digital programme, both revenue funding (focused primarily on data improvement and replacing our education case management system) and capital funding around our hardware refresh.
|  |  | A new ICT Governance Board has been established, including the Leader, Deputy Leader and Chief Executive. This board will provide oversight of the highest priority elements of the Council’s ICT transformation as well as making sure there is corporate oversight of the Council’s ICT improvement journey. (Includes One programme) | Director of People and Digital Services | Terms of reference have been drafted Oversight of risk is a priority | The Board is in place with a focus on shaping digital priorities and investment as well as high risk programmes including our data intelligence journey, the One Programme and cyber security. | Now the board has been in place nearly 12 months, terms of reference and role are under review with increased focus on oversight of the new Digital Strategy and digital innovation as well as the high risk programmes.
|  |  | A new digital strategy is being developed that will set out the roadmap and investment needed for the next 4 years | Director of People and Digital Services | Digital Strategy Approved by Cabinet (Dec 2024) Delivery Plan agreed | There has been significant work to co-produce the strategy to ensure aligns with council ambition and requirements. Approval now planning for December Cabinet. | On track for approval at December Cabinet (update - now approved)
|  |  | The results of the latest Staff Survey are currently being analysed and will be used to develop and hone plans for workforce health and wellbeing. Will track this theme across results of the survey. Highlighting the questions/ responses which linked to this recommendation. In particular analyse the free text responses to drill down into key issues. | Assistant Director for ICT | An action plan will be developed in collaboration with Digital and ICT service (DICT) to specifically tackle the issues highlighted in the responses. Evidence will be found in the specific reference to the frustrations with DICT in the resilience and wellbeing offer to staff. | Governance meetings with CEx, Deputy CEx, Monitoring Officer, Director of Digital and People, Leader and lead member to provide assurance and governance over key digital projects ie One Programme now monthly. | Governance meetings continue to take place on a monthly basis. The Digital Help Hub provides same day support and has a 100% satisfaction score. Improvements to the core infrastructure and replacement of legacy technology has improved the day to day experience for staff.
|  |  | Creation of a Project and Change Management Portfolio Management Office ('PMO') forum group, to share best practice and skills - including Transformation approaches and language referred to in the report (transformation/Improvement/Business As Usual) | Director of Policy, Performance and Governance | First meeting Feb 2024, agenda and discussion points will be recorded along with improvement actions. | 2 successful 'hybrid' forum events have now been run, with attendance of around 80 individuals at each, and recording available for others. It has developed a 'community of practice' around our Portfolio Management Office and change management, and feedback for the discussions and involvement has been excellent. | The third forum has been arranged for April 2025. This forum has become a well regarded event, designed to bring colleagues together from across the projects and programme management community. It is now an established part of the business as usual rhythm of stakeholder engagement, promoting and sharing how change is approached across the council.
3 | Ensure the equalities, diversity and inclusion (EDI) agenda is ‘lived and breathed’ by the entire cohort of leaders | Director of People and Digital Services | Additional corporate capacity is being created to continue to deepen and develop our approach to Equalities, Diversity and Inclusion, including increased support for staff networks. | Director of People and Digital Services | When additional capacity/resources are identified and in place | x2 new Policy Officers have started | Clear work programme in place for new officers reporting to the Equality, Diversity and Inclusion board with increased Corporate Leadership Team focused on the work. Currently fixed term so starting conversations about how to embed that permanently.
|  |  | Work on uncovering route of concerns Will track this theme across results of the survey. Highlighting the questions/ responses which linked to this recommendation. In particular analyse the free text responses to drill down into key issues. | Head of Organisational Development | An action plan will be developed in consultation with Employee Voice Groups (EVG) and Employee Networks to specifically tackle the issues highlighted in the responses. Facilitated workshops to collaborate with EVG groups and Employee Networks to explore the root cause and co-author potential solutions. | Work Planning Chairs Forum session scheduled for 30 September 2024. All Directorates committed to running a minimum of x3 Employee Voice Group meetings each year. March April was focused on survey results and action planning for each directorate. June July - focused on finalisation of action plans and approval/progression of these plans. | Third round of Employee Voice Group meetings of the year are happening Nov/Dec - focus is on ongoing progression of directorate action plans. Continued focus on Equality Diversity and Inclusion tea talks for all networks providing valuable insight to help continue to shape areas of improvement. Equality, Diversity and Inclusion pulse survey questions have been created to better understand our underlying issues, these questions will be included in the 2025 staff survey in January and will form part of a deep dive. Action plans within each group are updated at each meeting, with a focus on the importance of co-authorship and co-creation of solutions.
|  |  | Wider cohort of senior leaders become sponsors for EDI agenda - for example being sponsors for the employee networks. We name leaders against the LGA best practice framework and action plan. Specific leaders names as owners Currently working up a wider mandatory EDI training programme, this will be developed to have a new focus for senior leaders. | Director of People and Digital Services | All networks to have senior leader sponsor EDI training for leaders developed. EDI training for leaders attended by all senior leaders. Outcomes should feed into staff survey responses above. | All networks have a senior leader sponsor, including the new Women's Network. A review of our Equality, Diversity and Inclusion (EDI) training has taken place and an EDI learning pathway is in development. A new course for Senior leaders will be developed with enhanced focus on behaviours. The EDI learning pathway has been approved by Corporate Change Delivery Group and whilst there will be increased focus on driving up completions there is a dependency on the new Learning Management System to properly implement and embed this pathway. A Corporate Leadership Team paper that focused on increasing senior diversity was approved, including the approval that all Reward Band (RB) employees are to attend EDI training, An EDI training completion audit of the RB population is underway. CLT have attended anti racist training, the Director of People and Digital Services is discussing next steps for onward cascade of this content | All Executive Directors are active in Employee Voice Group meetings and driving directorate action plans and are participating in Network Tea talks. Increased time at Corporate Leadership Team (CLT) to focus on Equality, Diversity and Inclusion (EDI) agenda, half day anti-racism development for all of CLT, time on every Leadership Conference on EDI with recent focus on leadership framework and behaviours. Recent EDI board has supported ensuring a wider representation of senior leaders attend tea talks. The EDI learning pathway has been approved by Corporate Change Delivery Group and whilst there will be increased focus on driving up completions there is a dependency on the new Learning Management System to properly implement and embed this pathway.
4 | Enable greater collective corporate leadership and the development of cross-organisational dialogue, understanding and approaches | Director of People and Digital Services | Corporate Leadership Team (CLT) development sessions spring 2024: "Shaping the CLT culture - 'how we work around here' This will inform the decision and approach to organisational development. Programme of development sessions which agree a programme of work 24/25 to agree how we will respond long term. A shared understanding of our key ambitions, organisational design and methodology for aligning priorities with strategy." | Director of People and Digital Services | Initial sessions completed. Workplan in pace for organisational development. A reviewed 4 year MTFS process for this year (item 8 below) and this will be used as a way to implement | The development programme is in place and progressing to plan. The Medium Term Financial Strategy process has been shaped based discussions regarding how Corporate Leadership Team want to work as a leadership team with a review planned for early 2025. | First year plan completed plus an additional specialist session on anti-racism. Medium Term Finacial Strategy process reflected improved 'first team' focus. Review of the year underway with view to developing next stage of programme for 2025.
|  |  | Prioritisation support: What are we doing to safeguard our staff health and wellbeing in a highly pressurised environment. | Head of Human Resources | Ongoing development of the new Health and Wellbeing (H&WB) Strategy, including a new model that will be running by November '24. The new model will provide a out-reach/ targeted service, focused on where there is a known or emerging issue in teams. This will compliment established H&WB processes which are already in place. | New model in Occupational Health is fully recruited to and a draft operating model for the new wellbeing and mental health leads has been developed. Draft strategy based on a workshop with key stakeholders has been developed and positively received by the Health and Wellbeing Group and Corporate Exec Director sponsor and will now progress through the approval process. Within HR some new temporary resource is being recruited to review our organisational approach to sickness, associated resources and tools for managers and manager support. | Prioritisation workshop held in October 24 by the DIrector for Policy, Performance and Governance with senior Corporate Resources officers. Prioritisation identified as a key objective in the Directorate Plan for 24/25. Health and Wellbeing Strategy has been completed and approved. A survey and workshop specifically focusing on health and wellbeing for senior staff has been launched so we can better identify and target the challenges for senior staff. Temp support now in place within HR undertaking a project rethinking the approach to sickness absence, upskilling managers etc.
|  |  | Support and promotion of wellbeing resources. There will also be a key line of enquiry for CLT in the development sessions above - how will we respond to the challenge of prioritising more. Match our resource and prioritisation methodology. CLT prioritising and leading the organisation. | Director of People and Digital Services | Part of the workplan in 4a - specifically around prioritisation and planning. | Weekly section on wellbeing and support embedded into Talk smart, new wellbeing adviser in place. Workshop around how we prioritise arranged. | New Wellbeing Strategy developed and agreed by Corporate Leadership Team in November. Workplan in place for 2025. Focused Scrutiny review planned for Feb 2025.
|  |  | A review of the scale of Performance monitoring and reporting: This will begin in May 2024 to ensure the value added by reporting at the different conversation levels, and how that enables cross cutting support and challenge. | Head of Planning, Performance and Insight | Session in May 24 will lead to follow up actions | Initial review complete along with survey of CLT views. Initial changes to reduce breadth of coverage and increase focus on priorities is being trialled. Report to Nov Performance CLT includes updates and additional recommendations, although work with new Cabinet to review reporting is likely to affect this. | New Cabinet dashboard reporting has taken the lead in this area. Key performance measures are being reviewed directly by Cabinet with Directors and the performance and improvement team. Resources are being set up to deliver this as quickly as possible, but will set up the direction of travel for new council strategy reporting due in the coming year (timing dependent on local elections).
5 | Demonstrate to people within the organisation that they are being heard and responded to (particularly in relation to the way the Council determines its priorities) | Director of People and Digital Services | Staff survey Results will be published in March - EVG groups will have these in March. Results are going to team leaders now. | Head of Organisational Development | Partnering with Comms to do a 'They said - We did" piece. Employee Voice Group discussions are booked in and will lead to action plans. | You said we did' communication was completed as part of pre launch campaign. Results were shared with EVGs in March and action planning commenced. Follow up meeting took place in June/July to finalise and approve action plans and also complete progress checks. Plans have been published on SharePoint and next EVGs are Oct/Nov. This cycle will repeat for the next staff survey | 2024/25 staff survey is planned to go live Jan 2025. A review of the staff survey questions has taken place to create an annual data set. The survey is currently being built. Action planning will now be a rolling 12 month plan of continuous improvement. Enhanced communications campaign is currently underway as part of the warm up coms plan for each directorate to profile their key achievement. this is being communicated via "You said", "We did" messaging in Talksmart and local directorate newsletters.
|  |  | Employee Voice Group (EVG) review. EVG groups will help to develop the action plans at the Directorate level. Ensure we optimise the EVG forums, hold workshops to collect targeted feedback from the EVG groups on the 'people centric' action plan recommendations. Asking what do they think our organisational response should be? | Head of Organisational Development | Further iteration of the comms plan. Drilling down into the anecdotal evidence. Key aim will be to increase confidence that we are responding appropriately. Evidence of the feedback from these forums will be visible in the relevant action plans which are developed. | EVG review progress - awaiting update There have been two EVG meetings held this year, March/April to review how well EVG groups are working, to discuss results and to commence action planning. June/July to finalise action plan and complete a review progress. Next EVG Oct/Nov 24. | Employee Voice Group (EVG) meetings are working well. the third EVG group meeting of the year are happening now (Nov/Dec) - focus is on ongoing progression of directorate action plans. It has been agreed that all directorate action plans will become a rolling programme of continuous improvement.
|  |  | CLT to agree up to 10 priority actions for the year and commit to regular comms via multiple routes on how we are following up. | ownership revised following discussion at CLT and new Cabinet (Rob Ayliffe) | Updated following new Cabinet and re-aligning of priorities | Awaiting new Cabinet from September 24. | Cabinet/Corporate Leadership Team away day held to review priorities for coming 6 months, and undertake some analysis of trends and priorities for the longer term (subject to the outcome of next year's Council elections)
|  |  | Q&A follow ups to staff survey. | Head of Organisational Development/ Head of Communications | A CLT Q&A follow ups booked and delivered. | Council wide action plan and Directorate actions plans have a commitment to increase visibility of senior leaders and to run Q&A or similar type sessions with updates to staff a minimum of twice yearly. CLT approval of plan July 24. Plans have been now been published on SharePoint. | Ongoing Q&A sessions are being run locally by directorates.
|  | Director of Policy, Performance and Governance | Corporate approach to resource allocation - CLT PMO sub group (Coproate Portfolio Management Group) is in planning stage, to oversee cross-cutting delivery of priorities and use of resources corporately. | Head of Planning, Performance and Insight | First meeting and completion of Tor and reporting by end of May 2024. | 2nd meeting held and moved forward on prioritisation discussions, and how to gain oversight of key activities. Links made to prioritisation workshops referenced below. | Significant progress in bringing three themes of this work together - the MTFS organisational approach, the review of prioritisation techniques and resource allocation, and the application of transformation resource. Progress is being overseen currently by the Corporate Resources extended management team along with the Corporate Portfolio Management Group (CPMG), set up in response to this issue, and led by the Exec Director of Corporate Resources.
|  |  | Learn from other Council's approach to prioritisation and bring a report to an early meeting of the above group about a proposed approach | Head of Planning, Performance and Insight | Discussion at CLT PMO sub-group and subsequent actions agreed | Terms of reference done, prioritisation options shared and discussed, with a report on breadth of current activity and oversight of resources allocated. October meeting to bring focus onto how to establish resource limitations. Wider workshop on prioritisation booked October 24, and MTFS discussions on emerging priorities and impact on resources also planned with Corporate Resources leads. | Workshops held in October have led to key themes being developed, and worked up by service heads through November. These will be taken forward by the CPMG (see above) and Corporate Resources management team, and include improved collective oversight, a review of Business Partner engagement to raise emerging issues/conflicts sooner, and skills development for staff.
6 | Enable a greater focus on prioritised outcomes for communities through the more effective use of cross-cutting data and intelligence | Director of Policy, Performance and Governance | Develop a Data and Intelligence Strategy to sit alongside / within the Digital Strategy: Developing the necessary skills, culture and investment to take us to the next level in our data and intelligence usage. | Head of Planning, Performance and Insight | Draft Data Strategy developed and shared with Digital Governance Board and other key stakeholders (NB - this may not be in time for November, but will be well on it's way) | Strategy complete, signed off at Sept Cabinet, launched with new Programme framework in October 25. Strategic Lead resource begins in October to develop roadmap, but significant elements are already well underway. | Strategy complete and signed off. Leadership conference launch on 13th November, and new governance being set up ahead of MTFS resources commitment in March 2025.
|  |  | Continue to develop and deploy Power BI dashboards, which change the accessibility and usage of live data for decision making. | Head of Planning, Performance and Insight | Adults, Children's and Joint Strategic Needs Analysis (JSNA) reporting suite completed and launched. | rollout continues and now forms part of the wider programme to deliver the new Data and intelligence Strategy (Cabinet 18th Sept). Technical delays and some data gaps identified within ASC ahead of the CQC visit in September, but a roadmap of work to resolve and resources to support it, is in place. | Links to above, as new roadmap will now take this into the strategy work - but thematic groups are being developed for all Directorates to ensure roadmap and benefits realisation is in place. On overall governance structure with Member involvement is also being set up to oversee outcomes and resource application.
|  |  | Review Data & Analysis (MAIDeN) partnership with District Council colleagues - this offer forms the basis of shared open data with partners and communities. | Head of Planning, Performance and Insight | Scope and future direction of partnership agreed and funded. First meeting due March 2024. | Review complete and all members rejoined, with refreshed outline of purpose. | complete
|  |  | Launch pilot of data academy apprenticeships for skills development. | Head of Planning, Performance and Insight | Initial pilot of apprenticeships launched likely June 2024) | First 6 monthly review of apprenticeships in October 2024, ahead of re-procuring options for 2025. Wider work on skills now being made part of the Data and Intelligence Strategy work plan. | pilot reviewed and shows significant success, with 33 out of 37 initial apprentices remaining on course and delivering self declared efficiencies in data application. A second round is in development, along with a raft of shorter term training to be invested in when MTFS funds come available in 2025.
Additional Recommendations:
7 | Elected Member and scrutiny development. | Director of Policy, Performance and Governance | Develop and Agree protocol on keeping councillors informed on local issues | Director of Policy, Performance and Governance | Protocol approved by Constitution Committee | Protocol approved by Constitution Committee subject to minor amends in January 2024. | Protocol disseminated to senior staff and councillors. Additional training provided to some staff groups where particularly relevant
|  |  | Run ‘marketplace’ event to provide councillors with an opportunity to meet with a range of senior officers, find out more about Council services and fill gaps in their knowledge and understanding of how the council works. | Head of Democratic Services | Event run (May 2024) Evaluation of event and lessons learnt for incorporating into plans for new Council induction (August 2024) | Marketplace event successfully carried out in May 2024. Member Induction plan for 2025 being drafted based on the feedback from this event and a Member development survey circulated in June 2024. | Member Induction Plan to go to Corporate Leadership Team in December. Member Market Day event included.
|  |  | Improve scrutiny work planning - Create a quarterly scrutiny chairs forum to encourage collective review of the forward plan, and proactive work planning across scrutiny committees (by September 2024) | Head of Democratic Services | Created by Sept. Plan 4-yearly review of scrutiny arrangements (Proposals for review brought to COSC in November 2024) | Work Planning Chairs Forum session scheduled for 30 September 2024. | Scrutiny Forum held on 30 September. Additional Forum meeting scheduled for early 2025 and will include the review of scrutiny feeding into the election 2025.
|  |  | Introduce earlier publication of Cabinet and Cabinet Member decisions onto the forward plan | Director of Policy, Performance and Governance | Increased number of items published on forward plan at least 3 months before decision date | New processes in place but still working with Directors to embed | Arrangements now in place. Directorate Leadership Teams reviewing monthly to ensure new items are identified and added as appropriate.
8 | Extend the horizon for thinking around addressing the financial challenge. | Executive Director of Corporate Resources | A refreshed MTFS process has been programmed for this spring/summer to deliver a fuller 4 year horizon plan for 2025/29. | Director of Finance | Process formed and communicated by June 2024. Directors to work on initial proposals with a series of Budget Panels in September and October. Will be running and showing progress for reporting in Sept. 2024. | The MTFS process has been redesigned to put more focus on the full 4 years of the MTFS rather than focus on the following financial year. Directorate workshops have been completed and the Resource Planning Panels will commence in September 2024. | The initial Medium Term Financial Strategy (MTFS) phase of the refreshed MTFS process is nearly complete. The draft consultation budget shows detailed proposals over the 4 year planning horizon. This is due to go to Cabinet on 4th December prior to a period of public consultation.
9 | Celebrate success | Director of People and Digital Services | We have begun to plan the return of our annual staff awards event for 2024 to celebrate achievements and successes. These are linked to the core organisational values. They are non-hierarchical and all staff, all projects can be nominated. Celebrating good work, good ethos, good team relationships. | Head of Organisational Development | First of the new look Staff Awards event will have run by Nov '24. This will be a good news story to share. We will be able to gather feedback from attendees on how it impacted them and ideas to build into next event to demonstrate continuous improvement and collaboration. | Done Celebration ceremony took place in June with really positive feedback. Evaluation of the event and learning review has taken place. A review of the recommendations for any change is underway. A commitment has been made in the Council wide action plan for this to be an annual event. Together with an additional action to provide managers with tools to help managers do recognition well. | A discovery survey has been undertaken to better understand at a corporate level what is happening across GCC, what tools are being used and the value that staff place on these. Analysis of this feedback is underway. WC: High level planning for 2025 annual awards ceremony is underway and provisional date of 25th June has been set for the celebration event and approved by Corporate Leadership Team.
|  |  | Comms around the staff survey: Suggested plan for the comms, stagger review points. Use KEY achievements (3months, 6m 9m etc etc) Head of Communications to collaborate with Head of Organisational Development - this approach will highlight continuous approach to change and comms to celebrate. | Head of Organisational Development | By November all results will be out and action plans will be underway and implementation will be underway. | All Directorate and Council Wide action plans have been created. Nina has initiated a quarterly review on progress, the first of which takes place in August. The date for next years survey will be finalised in August and a coms and engagement plan will be created to support 24/25 survey which will be phased for each directorate to play back their achievements. | Recognition has become a key feature in both corporate and directorate local newsletters to celebrate success and provide recognition. Enhanced communications campaign is currently underway as part of the warm up coms plan for each directorate to profile their key achievement. this is being communicated via "You said", "We did" messaging in Talksmart and local directorate newsletters.
Note on B3: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Report context: An engagement process around the devising of a five-year economic development strategy ran through the summer this year and the aim is to see the final version adopted in early 2024. It will feature a set of actions to deliver a strong and inclusive economy for communities and businesses, along with a series of topics such as inward investment; business support; digital; zero carbon; inclusive growth; skills and employment; and sustainable growth. The emerging strategy, being led on by the council and GFirst, is coming to be seen as an alternative for the Vision but, by definition, is neither as broad nor as comprehensive. In this context, we would recommend the council build on its strategic leadership role to work with partners to shape the evolution of a refreshed vision for growth in Gloucestershire.
Note on D4: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Report context: The style and approach of the council in how and where it engages forms strong perceptions amongst partners. Whilst, as we have outlined, there is much that is good in how they work together, tensions clearly exist between the county and the district and borough levels in Gloucestershire. These seem to be centred on the approach to Local Plans, Community Infrastructure Levy and Section 106 funding contributions.
Note on D5: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Context from report: The transition from the LEP needs to continue to be carefully managed in order to ensure that the council maintains the strong links and relationships that GFirst has established with the business sector. There is a similar consideration in relation to the six Growth Hubs as the funding mechanisms around the UK Shared Prosperity Fund, which has been integral to their creation, change. There is a Growth Hub in each of the district and borough council areas, focused on supporting local businesses to develop.
Note on B7: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Report context: Adequate capacity needs to be dedicated to ensuring appropriate assurance around the driving of improvement in key ‘corporate enablers’ centred upon ICT, digital and data and intelligence. We noted, for example, that the ‘One Programme’ and similar initiatives seem to be subject to less scrutiny, although their successful delivery is key to the future success of the organisation. It is important for the council’s assurance mechanisms to identify issues as they emerge and ahead of any requirement for more major improvement being identified. Reply: 2nd reference: The ICT infrastructure across the organisation is impacting significantly on its effectiveness with some staff reporting it is even impacting their health and well-being. It is recognised that things have improved during the course of the last couple of years but even with the major investment that has been made, issues still exist. The necessary further improvement must be made a more demonstrable corporate priority and we recommend that the council prioritise continued investment in ICT as an enabler to the council’s operations. This includes ensuring the associated funding, expertise and leadership needed for the future are established and the driving forward of this, including the ‘One Programme’ and work on the customer and digital, is made an equal part of the council’s overall transformation portfolio along with children’s services, Fire and Rescue and adults services. There also needs to be a clearer narrative for staff and councillors about what has been delivered already in the way of ICT improvement and the roadmap for further progress.
Note on D7: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Context: The ICT infrastructure across the organisation is impacting significantly on its effectiveness with some staff reporting it is even impacting their health and well-being. It is recognised that things have improved during the course of the last couple of years but even with the major investment that has been made, issues still exist. The necessary further improvement must be made a more demonstrable corporate priority and we recommend that the council prioritise continued investment in ICT as an enabler to the council’s operations. This includes ensuring the associated funding, expertise and leadership needed for the future are established and the driving forward of this, including the ‘One Programme’ and work on the customer and digital, is made an equal part of the council’s overall transformation portfolio along with children’s services, Fire and Rescue and adults services. There also needs to be a clearer narrative for staff and councillors about what has been delivered already in the way of ICT improvement and the roadmap for further progress.
Note on D8: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: This includes ensuring the associated funding, expertise and leadership needed for the future are established and the driving forward of this, including the ‘One Programme’ and work on the customer and digital, is made an equal part of the council’s overall transformation portfolio along with children’s services, Fire and Rescue and adults services.
Note on D11: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: It was widely acknowledged during our discussions that there is a lack of clarity around what respectively represents ‘transformation’, ‘improvement’ and ‘business as usual’ within all of this activity.
Note on B12: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Report context: The EDI agenda has made much important progress and this is hugely welcomed by staff. There is a lot of work being delivered particularly at Staff Network level and the agenda has generated huge engagement. The council undertook a self-assessment against the Equality Framework for Local Government last year. This has led to the development of an action plan with four objectives: Improve the quality and consistency of service user data and workforce equality characteristics Develop an infrastructure that enables the council to hear from communities and engage effectively with them Embed EDI within the council’s culture and ways of working Strengthen leadership, oversight and governance of EDI across the council Much of this links closely with our recommendation of there being an on-going demonstration of greater join up around EDI and it being ‘lived and breathed’ by the entire cohort of leaders in order to help cement it as a priority in the organisation.
Note on B15: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Report context: At the senior managerial levels, there remains a sense of the leadership focus being on service and Directorate-based functional ‘domains’ rather than collective leadership. There is still a ‘journey to go on’ in developing cross-organisational dialogue, understanding and approaches. There was an appetite for seeing this and being involved in it amongst some of those we spoke to immediately below the senior-most managerial leadership levels. Aspects of this include developing more corporate approaches to addressing the council’s budget challenges and determining how the finite support available from key corporate functions, such as finance, communications, legal and HR, comes to be deployed to greatest effect. Reply: Further context: A good example of a corporate approach to key support activities was the collective determining of a council communications strategy at CLT level. This, however, was followed by Directorate-based discussions on their priorities under this umbrella, which served again to create a situation in which the corporate function was left to determine whose needs would be prioritised. Another example relates to the procurement function, which represents one of the council’s strategic priorities for improvement. The authority has recently recruited expertise to lead in this area and this has been widely welcomed. However, a risk-based capacity review looking at determining the procurement needs of the wider organisation and how these could best be supported has again created a situation in which that function is left to determine the priority order of things. There is also a general frustration on the part of corporate support functions that their expertise is often sought ‘late in the day’ rather than being woven in at the outset of a service or Directorate’s thinking. Reply: Mandy has discussed next steps coming out of the insight session with Pete, so should be able to populate this section of the action plan
Note on D16: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: A number of staff groups reported feeling very stretched and yet the pressures in Gloucestershire feel to be similar to elsewhere in terms of demand, complexity and workforce and the council is relatively well positioned in terms of its resource-base. This suggests that prioritisation should come to the fore as a key issue for the organisation, along with addressing the underlying ICT issues which are impacting capacity. Reply: Preventative approach to stress and anxiety - establishing a more preventative approach, centred on helping people prioritise workloads and ensuring they ‘have the tools to do the job’, would be preferable. Linked to this, the authority will wish to be mindful of the need to ensure identified and agreed ‘reasonable adjustments’ to people’s working arrangements and facilities are consistently delivered in a timely manner.
Note on D18: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: the scale of monitoring and reporting around these boards and programmes, combined with on-going reporting of performance to the likes of Cabinet and CLT, is extensive and is absorbing significant capacity. Senior leaders will want to assess the sustainability of the existing arrangements given the intense demands this places on meeting time; that there is sufficient cross-council assessment of interdependencies between the programmes; and that the right issues are highlighted, heard, focused on and overseen at the appropriate level.
Note on B19: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Report context: There are some slight frustrations emerging around aspects relating to responsiveness where people are being invited to pose questions to senior leaders, including through Q & A sessions or dedicated e-mail facilities, but aren’t consistently receiving a reply. Some staff also highlighted difficulties in accessing and navigating Staffnet, the council’s Intranet facility. Reply: Further context: In relation to workloads, people indicated that when they raise this they keep being told that they “are being heard”. However, their experience is that little seems to change in relation to prioritisation and things stopping.
Note on D23: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Context: Key corporate support functions generally enjoy good relationships with Directorates. However, there is a fundamental question as to how finite corporate support comes to be deployed. Currently it would seem to fall to individual support functions to determine for themselves how best to cope with the requests being made of them for support from across the wider organisation. This places them in a rather invidious position and there is a desire to see more collective endeavour and strategic thinking in determining the priorities. This is central to the question the council posed us in terms of probing how effectively it is aligning its corporate resources to drive transformation and improvement organisationally whilst supporting improvement within specific areas. Individual corporate support functions should not be left to have to determine for themselves how they allocate their resource. There are also considerations around how effectively the corporate support functions are being enabled to operate, in a context of the ICT issues already highlighted. Reply: Further context: A good example of a corporate approach to key support activities was the collective determining of a council communications strategy at CLT level. This, however, was followed by Directorate-based discussions on their priorities under this umbrella, which served again to create a situation in which the corporate function was left to determine whose needs would be prioritised. Another example relates to the procurement function, which represents one of the council’s strategic priorities for improvement. The authority has recently recruited expertise to lead in this area and this has been widely welcomed. However, a risk-based capacity review looking at determining the procurement needs of the wider organisation and how these could best be supported has again created a situation in which that function is left to determine the priority order of things. There is also a general frustration on the part of corporate support functions that their expertise is often sought ‘late in the day’ rather than being woven in at the outset of a service or Directorate’s thinking.
Note on B25: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Context from the report: More widespread effective use of cross-cutting data and intelligence would help to drive different ways of working in the council, developing cross-organisational and targeted approaches focused on delivering prioritised outcomes for communities. A key element of achieving this seems to be around enabling people within the council to understand more “the art of the possible” in terms of what data and intelligence can offer. This is an element of the remit of the council’s Strategic Intelligence function that it would like to have the capacity to extend, providing insights to colleagues as to the potential that exists and helping to shift things from the council being “data busy to data-driven”. Crucial to this, though, is having the necessary ICT infrastructure in the council, with people highlighting a lack of confidence currently in the quality of the data available to them, in a context of system issues that we touch on in more detail later.
Note on D30: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Officer responsiveness to casework from elected members being seen to be inconsistent and some elected members highlighting ‘finding things out after the event’ in relation to their Division, thus putting them on the ‘back foot’.
Note on D31: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Elected member induction following the elections in 2021 is seen to have been intense. This, combined with the fact that it was undertaken during the pandemic, means there is some refreshing that would be good to undertake. In particular, elected members highlighted a desire to get to know senior officers more and to learn their way around Shire Hall better
Note on D32: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: There is, however, felt to be significant scope to develop the work of Overview and Scrutiny. Central to this is being able to focus more on what really matters in the county and the organisation. More co-ordinated work programming may have a role to play here with, as we understand it, each Committee currently determining its own activities.
Note on D33: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: We also noted the way in which the Forward Plan for the Executive is seen to have a limited time horizon, with it not routinely exceeding the 28 days limit to publish decisions in advance. This does not lend itself to Overview and Scrutiny being able to work programme to maximum effect and limits the scope for undertaking pre-decision scrutiny.
Note on B34: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Context: The potential also exists to extend the horizon for thinking around addressing the financial challenge. This would see, under the auspices of a more detailed MTFS, more in the way of ideas and proposals that may take a few years to come into being but on which work could start now. It would also enable a shift from what is a largely year by year approach to considering the budget currently. In positing this, we recognise that determining the financial position and medium-term funding challenge in any degree of detail is difficult for any council currently. This shouldn’t, however, curb the contributing and developing from across the organisation of longer-term ideas that would offer potential.
Note on B35: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: As we outlined earlier, we met a large number of talented officers and councillors who are hugely committed, are delivering much good work and are passionate about delivering services for the people and communities of Gloucestershire. In this context, it was surprising to glean that success doesn’t seem to be celebrated to any great extent in the organisation. There is much for the council and the people within it to be proud of and we would encourage the organisation to celebrate this more.